## Sheet1
WBS |  | Owner | Deliverables | Remaining hours | Base line hours | Deadline
| Charting resize | Tuan | Code tested |  | 20h | 2012-08-03
| Bug fix | Tuan | Code tested |  | 10h | 2012-08-03
| Data extraction | Huy, Dat | Code tested | 20h | 30h | 2012-08-03
| Reports requirement | DuyAnh, Thuy | Doc | 20h | 30h | 2012-08-03